## Sheet1
Sr.no | Task and Discription | Started | Ended | Status | GitPush
1 | Login Page - Create login page UI - Create Heard Create login form Add Login - Create User entity Add JWT Auth | 2026-08-14 | 2026-08-16 | Compeletd | Code Pushed
2 | Test Login page with backend using jwt aut
3 | Entity - Create Entities models and DTO's for all the entities - User Tenant Room Property Billing Auth Roles | 2026-08-17 | 2026-08-18 | Compeletd
4 | Services - Create service for all entities - API Auth Billing Property revenue room Sidebar tenant | 2026-08-19 | 2026-08-20 | Compeletd
5 | Test Data - Create test data for all entities - User Tenant Room Property Billing revenue | 2026-08-20 | 2026-08-20 | Compeletd
6 | Pages - Dashboard - Create UI for - Dashboard Side Bar Billing Properties Revenue room Tenants | 2026-08-21 | 2026-08-22 | Compeletd
7 | Set Ruting for all the pages | 2026-08-22 | 2026-08-22 | Compeletd
8 | Test UI and Funtion's of Dashboard | 2026-08-22 | 2026-08-22 | Compeletd
9 | Push code and deploy Application (Only Dashboard) to GiHub Command to push the code to GitHud(Branch - feature/login) - git checkout :- To know on which branch your are rigth now. - git status :- To check how many file are add to local repo and how many are remaining. - git add . :- To add all the remaining file's to local repo. - git commit -m "your commit" :- To commit all the newly added file's to local repo. - git push origin "branch name"(feature/login) :- Puch new commited code of local to remote repo's specifice branch. Command to deploy Angular application to GitHub (Run in cmd) - ng add angular-cli-ghpages(Only ones per project) :- adds GitHub Pages deployment support to your Angular project. - ng deploy --base-href=/"Name of the git repo"/(after every puch) :- build your Angular application and deploy it to GitHub Pages, while telling Angular that the application will be hosted inside the /RentalManagementSystem/ path. - command - ng deploy --base-href=/RMS/ | 2026-08-22 | 2026-08-22 | Compeletd
| Added fall back button for sidebar | 2026-08-23 | 2026-08-23 | Compeletd | Code Pushed
10 | Cross check, then Create or update Entity dto's as per requirment - Update Billing Entity (Added GenerateBillRequest DTO ¦ Updated BillingResponse DTO, BillingModel Entity) - Update Property Entity (Added PropertyType ENUM, RegiesterPropertyRequest DTO) - Update Room Entity (Added RegisterRoomRequest DTO ¦ Updated RoomModel (currentOccupancy)) - Update Tenant Entity (Added IdType ENUM, RegisterTenantRequest ¦ Updated Tenant Entity, Tenant Request, Tenant Response) - Update User Entity (Added Roles ENUM,RegisterUserRequest ¦ Updated UserResquest DTO, UserResponse DTO) - Solved Error occured after the changes. | 2026-08-23 | 2026-08-24 | Compeletd
11 | Create .md Documentation for Entity Modules and DTO's | 2026-08-24 | 2026-08-24 | Compeletd
12 | Page - Create Add Property button and form to create a property. - Added form for register property. Create Add Room button and form to create a new room. - Added from for register room. | 2026-08-25 | 2026-08-27 | Compeletd
13 | Create and update API services for all the entities as per requirment - Updated Billing Service - getBillByPorpertyIdTenantIdRoomIdMonth(), createBillByRoomId() - Updated Property Service - getAllPropertyByOwnerId(), createProperty() - Updated Room Service - getAllRoomByPropertyId(), createRoom() - Updated Tenant Service - getAllTenantByTenantIdUserIdRoomIdPropertyId(), createTenant() Updated Entity - Updated Billing Entity - Added class BillingRequest. - Updated Room Entity - Added class RoomRequest, Updated class RoomUpdateRequest. - Updated Tenant Entity - Added class TenantRequest, Updated class TenantUpdateRequest. | 2026-08-27 | 2026-08-29 | Compeletd
| Pages - - Update Property page - Removed the 'Total Room'. - Add dropdown css for 'Add Property' and 'Add Room' form. | 2026-08-29 |  | Standby
14 | Push code and deploy Application to GiHub - Updated Dash Board | 2026-08-29 | 2026-08-29 | Compeletd
15 | Pages - - Update Tenant pages - Update Serach by name and filter by Property function. - Add clickable rows to the tenant table(after clicking open tenant deatils page). - Add Tenant details page. - Add Create Tenant button to the tenant page - Add Create Tenant page | 2026-08-30 | 2026-08-31 | Compeletd | Code Pushed
16 | Pages - - Enhanced UI of Nave bar for android and windows. - Add amination for the porperty, tenant, side bar and login page. - Update font to "Plus Jakarta Sans". - Create a SnackBar service for login page. - Added animation to the property's card info. - Added animation to the tenant's card for android and tablet. | 2026-09-01 | 2026-09-03 | Compeletd | Code Pushed
17 | Pages - - Create page called bashboard where all the info realated to the owner will be disblayed. - Added dashborad.model.ts in core/models - Added dashboard.service.ts in core/service - Added test data in core/test-data and updated index in core/test-data - Added Overview page in pages/dashboard - Added animation to the overview page | 2026-09-03 | 2026-09-04 | Compeletd
18 | Pages - - Update the module of Billing(from scratch). - Added billing-generated and billing-pending tab to Billing module. - Added bill-details mdoule. - Added generate-bill form to generate bill. - Added generate-this-months-bill button and view-this-months-bill button to the room-details card. | 2026-09-04 | 2026-09-06 | Compeletd
19 | Pages - - Updated alignment to the billing section. - Added animation to billing section. - Updated minor variable of billing section. - Improve the animation of side bar in windows screen. | 2026-09-06 | 2026-09-07 | Compeletd
20 | Update animation of side bar for android (Working) | 2026-09-06 | 2026-09-06 | Compeletd
21 | Pages - - Added User signup page and connected to the user signup button on login page. - Removed Tenant Signup button from login page. - Test signup feature. - Added Back button to the Tenant Signip page. - Added animation to the user signup page. | 2026-09-10 | 2026-09-10 | Compeletd | Code Pushed
22 | Code - Code Review and removing unwanted code. Component Reviewd,Commented and finilized for code push - Login - Header - User signup - Dashboard/Overview - Dashboard/Porperties - Dashboard/Porperties/Add-Property - Dashboard/Rooms - Dashboard/Add-Room - Dashboard/Room-Details - Dashboard/Tenants - Dashboard/Add-Tenant - Dashboard/Tenant-Details - Dashboard/Billing - Dashboard/Billing/pending - Dashboard/Billing/generated - Dashboard/Billing/generate-bill - Dashboard/Billing/bill-details Update error messages for login form - Login component - User signup component - Add property component - Add room component - Add tenant component Added Location service to user signup component. | 2026-09-15 | 2026-09-16 | Compeletd